## Sheet1
DRAFT (June 2026)
SKILLS CANADA BC - RISK REGISTER
GROUP | RISK | LIKELIHOOD | RISK ANALYSIS | ACTION REQUIRED FOR RISK | RISK MITIGATION | RISK OWNERSHIP | RISK STATUS
Cyber security | Loss of onlinecomputer files | ?? | High | Review current cybersecurity levels | Need to assess level of risk | Executive Director | needs assessment
| Corruption of website | High | High | Review current cybersecurity levels | Need to assess level of risk | Executive Director | needs assessment
Reputation / Goodwill | Improper volunteer actions with youth | Low | High | Review other Province actions on said risk | Volunteers to never be alone with competitors | Board | Looks to be addressed adequately in comparing to other Skills Provinces
| Improper Board interaction with youth | Low | High | Ensure board code of conduct signed by all members | Add line to board application "Can you pass a criminal records check?" | Board | Working to finalize board handbook, code of conduct
Relationship Management | Reduced resources, limited opportunities, mission compromise | Low | Medium | Develop annual Executive Director action plan | Stakeholder engagement, relationship management, performance monitoring, communication protocols | Executive Director / Board Executive | Needs to be addressed
Economic Impacts | Misuse of funds | Low | Medium | Ensure adequate financial controls | Finances reviewed by internal accountant as well as audited | Board | Well controlled
| Lack of adequate accounting controls | Low | Medium | Ensure adequate financial controls | Finances reviewed by internal accountant as well as audited | Board | Finalize policy/procedure manual
| Non-profit status | Low | High | Create Treasurer checklist | Review Auditor Report annually | Finance Committee | To be created
| Tax liabilities | Low | Medium | Create Treasurer checklist | Review Auditor Report annually | Finance Committee | To be created
| Loss of physical assets | Low | Medium | Ensure current asset listing is available | Let board know what assets the society owns, ensure addresses in ED succession plan | Finance Committee | Needs to be addressed
| Inability to fundraise adequately for main event | High | High | Need to raise adequate funds to cover competition and add to reserve funds | All board to be aware of concern, and take part in fundraising | Board | Regular meetings of Business Development committee and board updates
| Fraud/Theft | Low | High | Ensure fraud mitigation addressed with financial control policies | Ensure completion of policies and procedures | Finance Committee | Currently finalizing policies and procedures
Management | Employment issues (wrongful termination, unfair hiring practices, sexual harassment or discrimination) | Low | High | Create employee manual | Review manual and internal HR policies annually | Board Executive | Employment manual in process
| Board structure | Medium | Medium | Review board makeup to ensure variety and coverage of all skilled trades | Review board makeup annually - ensure active nomination process | Board Executive / Governance Committee | Still work to be done
| General management controls | Medium | Low | Delegation of authority to be created and signed, as well as finalizing other documents | Finalize policy/procedure manual | Governance Committee | Underway
| Loss of current volunteer group | Low | High | Ongoing checkins with current group from Dennis/Michelle to Sylvia | Ensure we have a backup plan | Board | Need to create backup plan
| Conflict of interest | Low | Low | Review conflict of interest in board manual | Add declaration to each agenda as consent item | Governance Committee | Need to update
| Emergency ED Succession | Low | High | Ensure creation of succession plan for ED | Request ED creates emergency success plan | Executive Director, Board Executive | Set timeline?
Safety & Health Incidents | Legal liability, reputation damage, increased costs, regulatory action | Low | High | Review that safety protocols are in place annually | Safety protocols, equipment maintenance, insurance coverage, staff training, emergency procedures | Executive Director | Well controlled